## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US-001 | As a developer, I want to set up the complete Python project structure with all required folders, configuration files, and dependencies so that development can begin with a scalable and maintainable architecture. | MUST HAVE | None | Muskan | 3- Completed
Sprint 1 | Sprint 1 | US-002 | As a developer, I want to integrate the ChatGroq large language model using LangChain and securely load API keys from the environment so that the application can generate intelligent responses. | MUST HAVE | US-001 | Muskan | 3- Completed
Sprint 1 | Sprint 1 | US-003 | As a user, I want specialized AI agents for code generation, debugging, documentation, planning, and project analysis so that each task is handled by an expert agent. | MUST HAVE | US-002 | Muskan | 3- Completed
Sprint 1 | Sprint 1 | US-004 | As a user, I want a coordinator agent that receives requests, identifies the appropriate workflow, invokes the required AI agent, and returns a unified response. | MUST HAVE | US-003 | Muskan | 3- Completed
Sprint 1 | Sprint 1 | US-005 | As a user, I want conversation memory stored in JSON so that previous interactions can be reused to provide contextual and consistent responses. | SHOULD HAVE | US-004 | Muskan | 3- Completed
Sprint 2 | Sprint 2 | US-006 | As a user, I want an intelligent decision engine that automatically classifies requests and routes them to the most suitable AI agent or enterprise tool. | MUST HAVE | US-004 | Muskan | 3- Completed
Sprint 2 | Sprint 2 | US-007 | As a developer, I want enterprise tools including file management and Python code execution so that the assistant can perform real development tasks. | MUST HAVE | US-006 | Muskan | 3- Completed
Sprint 2 | Sprint 2 | US-008 | As a developer, I want patch management, project analysis, and multi-file parsing tools so that existing projects can be modified and analyzed efficiently. | SHOULD HAVE | US-007 | Muskan | 3- Completed
Sprint 2 | Sprint 2 | US-009 | As a developer, I want execution tracking, logging, and validation mechanisms so that all tool executions are monitored, secure, and auditable. | SHOULD HAVE | US-007 | Muskan | 3- Completed
Sprint 2 | Sprint 2 | US-010 | As a project stakeholder, I want comprehensive testing, documentation, and a professional README so that the project is reliable, maintainable, and easy to deploy. | COULD HAVE | US-009 | Muskan | 3- Completed
Note on F1: Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 61 | 12 | 12 | 12 | 11 | 8 | 4 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-001 | T-001 | Create project folder structure | 2026-07-01 | 2026-07-01 | Muskan | Build | Done | 4 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | T-002 | Configure requirements and .env | 2026-07-02 | 2026-07-02 | Muskan | Build | Done | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | T-003 | Integrate ChatGroq | 2026-07-04 | 2026-07-05 | Muskan | Integration Test | Done | 6 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-003 | T-004 | Build AI agents | 2026-07-05 | 2026-07-07 | Muskan | Coding | Done | 8 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
US-004 | T-005 | Implement coordinator | 2026-07-07 | 2026-07-09 | Muskan | Coding | Done | 5 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-005 | T-006 | Implement memory | 2026-07-09 | 14-Jul-2026 | Muskan | Coding | Done | 4 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-006 | T-007 | Develop decision engine | 01-Jul-2026 | 14-Jul-2026 | Muskan | Coding | Done | 5 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-007 | T-008 | Implement file tool | 01-Jul-2026 | 14-Jul-2026 | Muskan | Coding | Done | 4 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-007 | T-009 | Implement code executor | 01-Jul-2026 | 14-Jul-2026 | Muskan | Coding | Done | 5 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-008 | T-010 | Patch tool & parser | 01-Jul-2026 | 14-Jul-2026 | Muskan | Coding | Done | 6 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-009 | T-011 | Logger & tracker | 01-Jul-2026 | 14-Jul-2026 | Muskan | Coding | Done | 5 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-010 | T-012 | Testing & README | 01-Jul-2026 | 14-Jul-2026 | Muskan | System Test | Done | 6 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on D2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on E2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on I3: This is the total task estimated in hours for all the user stories
Note on J3: Pending effort hours after completion of day 1 work
Note on K3: Pending effort hours after completion of day 2 work
Note on L3: Pending effort hours after completion of day 3 work
Note on M3: Pending effort hours after completion of day 4 work
Note on N3: Pending effort hours after completion of day 5 work
Note on O3: Pending effort hours after completion of day 6 work
Note on P3: Pending effort hours after completion of day 7 work
Note on Q3: Pending effort hours after completion of day 8 work
Note on R3: Pending effort hours after completion of day 9 work
Note on S3: Pending effort hours after completion of day 10 work
Note on T3: Pending effort hours after completion of day 11 work
Note on U3: Pending effort hours after completion of day 12 work
Note on V3: Pending effort hours after completion of day 13 work
Note on W3: Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 1 | Project structure setup took longer than expected. | Finalized folder structure and dependencies.
Sprint 1 | Day 2 | API key configuration issues. | Verified .env configuration and tested ChatGroq connection.
Sprint 1 | Day 5 | Prompt tuning required multiple iterations. | Refined prompts for better responses.
Sprint 1 | Day 8 | Agent integration conflicts. | Resolved import and routing issues.
Sprint 2 | Day 16 | Tool integration complexity. | Integrated Tool Manager and validated execution.
Sprint 2 | Day 18 | Patch tool parsing errors. | Updated parser logic and retested.
Sprint 2 | Day 20 | Testing failures in workflow. | Fixed bugs and all test cases passed.

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2026-07-01 | 2026-07-13 | Muskan | Improve sprint planning and estimate tasks more accurately. | Starting multiple tasks. | Daily code reviews and regular commits. | Prepared detailed backlog and task breakdown.
2 | Sprint 1 | 2026-07-01 | 2026-07-13 | Muskan | Increase unit testing during development. | Delaying testing until the end. | Using modular AI agent architecture. | Integrated PyTest earlier in workflow.
3 | Sprint 2 | 2026-07-14 | 2026-07-26 | Muskan | Enhance tool integration automation. | Ignoring minor warnings. | Maintaining documentation after each feature. | Added execution tracker and logger.
4 | Sprint 2 | 2026-07-14 | 2026-07-26 | Muskan | Improve prompt optimization. | Hardcoded temporary values. | Using secure environment variables. | Refined prompts and configuration.
5 | Sprint 2 | 2026-07-14 | 2026-07-26 | Muskan | Expand workflow testing. | Skipping edge-case validation. | Frequent integration testing. | Improved validation layer.
6 | Sprint 2 | 2026-07-14 | 2026-07-26 | Muskan | Optimize response time. | Unnecessary code duplication. | Maintaining clean project structure. | Refactored common modules.
7 | Sprint 2 | 2026-07-14 | 2026-07-26 | Muskan | Plan future enhancements. | Last-minute documentation. | Team communication and progress tracking. | Prepared roadmap for next milestone.