## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Muskan. | 2026-07-01 | Streamlit UI did not display AI responses correctly. | Sprint 1 | Muskan. | User Interface | Updated Streamlit rendering and session state. | 2026-07-01 | Closed | Verified successfully.
2 | Muskan. | 2026-07-02 | Coordinator Agent routed requests to incorrect AI agents. | Sprint 1 | Muskan. | Logical | Improved intent routing logic. | 2026-07-04 | Closed | Validated.
3 | Muskan. | 2026-07-07 | LangChain prompt templates loaded inconsistently. | Sprint 1 | Muskan. | Standards | Standardized prompt initialization. | 2026-07-08 | Closed | Verified sucessfully.
4 | Muskan. | 2026-07-09 | Conversation memory was not retained. | Sprint 1 | Muskan. | Logical | Integrated JSON memory. | 2026-07-10 | Closed | Verified successfully.
5 | Muskan | 2026-07-10 | Project Analyzer missed nested folders. | Sprint 1 | Muskan. | Logical | Implemented recursive scan. | 2026-07-11 | Closed | Verified sucessfully.
6 | Muskan. | 16-07-2026 | Decision Engine selected wrong AI agent. | Sprint 2 | Muskan. | Logical | Enhanced intent classification. | 17-07-2026 | Closed | Verified successfully.
7 | Muskan. | 18-07-2026 | Tool Manager selected incorrect tool. | Sprint 2 | Muskan. | Logical | Refined mapping rules. | 18-07-2026 | Closed | Verified successfully.
8 | Muskan. | 19-07-2026 | Code Executor failed for dynamic input. | Sprint 2 | Muskan. | Logical | Improved execution handling. | 20-07-2026 | Closed | Verified sucessfuly.
9 | Muskan. | 20-07-2026 | Patch Tool failed to modify code. | Sprint 2 | Muskan. | Logical | Enhanced patch parser. | 21-07-2026 | Closed | Verified sucessfully.
10 | Muskan. | 21-07-2026 | GitHub Tool integration issue. | Sprint 2 | Muskan. | Standards | Updated API integration. | 21-07-2026 | Closed | Verified succesfully.
11 | Muskan. | 21-07-2026 | Security Guard blocked valid requests. | Sprint 2 | Muskan. | Maintainability | Refined validation. | 22-07-2026 | Closed | Verified sucessfully.
12 | Muskan. | 22-07-2026 | Action Validator failed verification. | Sprint 2 | Muskan. | Logical | Improved validation. | 22-07-2026 | Closed | Verified sucessfully.
13 | Muskan. | 22-07-2026 | Execution Tracker missed logs. | Sprint 2 | Muskan. | Maintainability | Fixed logging. | 23-07-2026 | Closed | Verified sucessfully.

## Sheet2
Logical
User Interface
Maintainability
Standards
Others